## Sell
Product Name | Hishabee Business Manager Desktop | Test Start Date | 15 Feb,2022 | Test End Date |  | Developer Name |  | Browser | Chrome,Mozila
Created By |  | Tawhiduzzaman Pavel | Reviewded By |  | Ratul Tazul | Version | 1.3.23
Tester's Name |  | Tawhiduzzaman Pavel | Date Tested |  |  | Test Case(Pass/Fail/Warning) |  |  |  | TEST CASE SUMMARY
PASS
FAIL
Module | Test Case ID | Title | Steps/Action | Test Data | Expected Result | Actual Result | Status | Remarks |  | WARNING
TOTAL
Quick Sell |  | Design | Check QuickSell Over all Design |  | As per requirement | 1. Quick Sell and Product list Button color is matched with background color 2. Calender and Image Button color and design is not done as per requirement 3. In Mozila browser calender icon not visible and calender default time is showing one day previous 4. Marging paddind of text field and drop down are not ok | Fail
|  | Add Filter option | 1. Click on + button 2. Click the check box 3. Check if the options are added |  | Button should work and option added | Not done | Fail
|  | Quick Sell Full module Check | 1. Select Quick Sell 2. Enter Amount,description, mobile number,profit,date, upload image |  | Matched in Transaction List with all details | As Expected | Fail
|  | Keybord | Check full functionality |  | Working | As Expected | Pass
|  | SMS | Enter All Information with SMS Enable |  | SMS should Sent to Customer | 1. SMS text is not well written 2. SMS not deducted from balance | Fail
Product List |  | Search Product from product list | Enter Product Name |  | Should get the desired product | When Enter a product name in search bar then erase one or two alphabets, not getting all products. But when Erase all then get all products | Warning
|  | Category List Filter | 1. Click on the filter icon 2. Click the category checkbox |  | Should get the desired product | 1. Working but at first all category should be checked in. 2. Should have select all option | Warning
|  | Add Product For Selling | 1. Select Product from product list 2. Click on total products that are added on the bottom 3. Inrease the product count if necessary or delete product if required 4. Add discount if want 5. Click on payment |  | Should go to the payment option page Successfully | As Expected | Pass
|  | Add Product For Selling Special test case | 1. Select Product from product list 2. Click on total products that are added on the bottom 3. Inrease the product count if necessary or delete product if required 4. Add discount if want 5. Click on payment 6. Then go back one page and delete all products |  | Total amount should be Zero | 1. Shows total amount of previous incomplete order 2. When add product amount not added, only added product count | Fail
|  | Discount Field | Enter Discount amount |  | Should entered successfully and deducted from total amount | 1. Default "0 " reamins when customer click, so high priority of wrong calculation 2. Customer may confuse where to click | Fail
|  | Product List Scroll | Scroll product list to see product |  | Should work properly | In firefox product list over lapping with product titles | Fail
Confirm Payment | TC-068 | Cash | 1. Add products in cart 2. Click on total sell 3. Add discount if nedded 4. Click payment 5. Select Payment Option Cash 6. Add addition description and customer info then click pay |  | 1. Should added in Transaction list 2. When click in the list should show all info | As Expected | Pass | Checked in App
| TC-069 | Digital Payment | 1. Add products in cart 2. Click on total sell 3. Add discount if nedded 4. Click payment 5. Select Digital Payment option 6. Enable customer info and add 7. Click pay |  | 1. Should added in Transaction list 2. Should go to Digital Payment link page | 1. In Digital Payment customer information can be given twice which is unnecessary 2. without submitting final modal data is showing in transaction list. 3. Amount should not be editable in final modal 4. Should be disable 2nd mobal if customer info already given or data should auto fillup from first modal. | Fail
| TC-070 | Due | 1. Add products in cart 2. Click on total sell 3. Add discount if nedded 4. Click payment 5. Select Due option 6. Enable customer info and add 7. Click pay |  | 1. Receipt should show the customer name ,dew amount and received amount 2. Also will show in due list and Transaction list | Not working | Fail | Bappi bhai still woring on it
| TC-071 | Bkash/Nagad

## Expense
Product Name | Hishabee Business Manager App | Test Start Date |  | Test End Date |  | Developer Name |  | Device | Oneplus 8
Created By |  | Tawhiduzzaman Pavel | Reviewded By |  | Ratul Tazul | Version | 1.3.27 | OS | Android-11
Tester's Name |  | Tawhiduzzaman Pavel | Date Tested |  |  | Test Case(Pass/Fail/Warning) |  |  |  | TEST CASE SUMMARY
PASS
FAIL
Module | Test Case ID | Title | Steps/Action | Test Data | Expected Result | Actual Result | Status | Remarks |  | WARNING
TOTAL
Add Expense | TC-117 | Salary | 1. Select Employee or add New Employee 2. Enter Amount 3. Enter Reason and details 4. Upload Image and select date 5. Click Save | Click on Expense list | Salary should be listed in Expense list with all entered data. | 1. Select Employee Dropwown arrow is placed outside the textbox 2. Not working for Advance date | Fail | 1. Select Employee Dropwown arrow is placed outside the textbox 2. Not working for Advance date
| TC-118 | Purchase | 1. Enter amount 2. Enter reason of Expense 3. Enter Expense Details 4. Upload Image and select date 5. Click Save |  | Purchase should be listed in Expense list with all entered data. | Not working for Advance date | Fail
| TC-119 | Bill | 1. Enter amount 2. Enter reason of Expense 3. Enter Expense Details 4. Upload Image and select date 5. Click Save |  | Bill should be listed in Expense list with all entered data. | Not working for Advance date | Fail
| TC-120 | Rent | 1. Enter amount 2. Enter reason of Expense 3. Enter Expense Details 4. Upload Image and select date 5. Click Save |  | Rent should be listed in Expense list with all entered data. | Not working for Advance date | Fail
| TC-121 | Add Expense Category | 1. Click on Expense Category 2. Click Add Expense Category 3. Enter Expense Category Name 4. Click Save |  | Category Should be added | As Expected | Pass
| TC-122 | Edit Newly Created Expense Category | 1. Click on Expense Type and then click Edit button 2. Edit Category Name 3. Then Save |  | Category Name Should be Edited | As Expected | Pass
| TC-123 | Delete Expense Category | 1. Click on Delete button 2.Then Confirm Delete |  | Category Should be Deleted | As Expected | Pass
Expense List | TC-124 | Check List | 1.Click on Expense List 2. Select Day,Week,Month,Year |  | 1. All the Entered Expenses should be shown 2. Total Expense Should Shown in the first page and also breakdown in persentage 3. In Business Overview total Expense should be matched on selected date | 1. For month, Advance dated entries are not showing,as a result total is showing wrong data | Fail | Except Bussiness overview
| TC-125 | Rent Edit | 1. Click Rent Container 2. Click Edit 3. Edit amount,reason,details,image,date 4. Click Save |  | 1. Edited data for rent should be saved in list 2. Total expense should be edited in both list and bussiness overview | As Expected | Pass
| TC-126 | Bill edit | 1. Click Bill Container 2. Click Edit 3. Edit amount,reason,details,image,date 4. Click Save |  | 1. Edited data for bill should be saved in list 2. Total expense should be edited in both list and bussiness overview | As Expected | Pass
| TC-127 | Purchase edit | 1. Click purchase Container 2. Click Edit 3. Edit amount,reason,details,image,date 4. Click Save |  | 1. Edited data for purchase should be saved in list 2. Total expense should be edited in both list and bussiness overview | As Expected | Pass
| TC-128 | Salary | 1. Click Salary Container 2. Click Edit 3. Edit amount,reason,details,image,date 4. Click Save |  | 1. Edited data for salary should be saved in list 2. Total expense should be edited in both list and bussiness overview | Not working | Fail
| TC-129 | Delete Salary/Rent/Billl/Purchase | 1. Click the container 2. Click Delete 3. Click confirm |  | Should be Deleted from list and amount should be adjusted in all list and bussiness overview | As Expected | Pass
Total Cost |  | Total Cost | Check Total cost from the top left corner |  | Total Cost must be matched with the sum of expense list individual amount | Percentages breakdown are not in fraction, as a result showing more than 100% | Fail | Need to show atleast two digit after points

## Digital Payment
Product Name | Hishabee Business Manager App | Test Start Date |  | Test End Date |  | Developer Name |  | Device | Oneplus 8
Created By |  | Tawhiduzzaman Pavel | Reviewded By |  | Ratul Tazul | Version | 1.3.27 | OS | Android-11
Tester's Name |  | Tawhiduzzaman Pavel | Date Tested |  |  | Test Case(Pass/Fail/Warning) |  |  |  | TEST CASE SUMMARY
PASS
FAIL
Module | Test Case ID | Title | Steps/Action | Test Data | Expected Result | Actual Result | Status | Remarks |  | WARNING
TOTAL
Digital Payment Link |  | Check Link | 1. Copy Link from Digital Payment Link 2. Paste it any browser and go to the url 3. Fill all info and pay |  | Should work the url | As Expected | Pass
|  | Share Link | 1. Click on Share Link 2. Click All shop payment option/social media |  | Should work all social media | Sms should redirect to our sms marketing but its redirect windows message options | Warning
Create Link |  | New Link | 1. Click on New Link 2. enter Name, amount 3. Click Save 4. Share or Visit link |  | New Link should be created successfully | Link Created but in share option sms not redirecting to sms marketing | Warning
|  | Check New Link | 1. Click on the created link container 2. Check link url,created date, number,customer name,status 3. Copy url and go to the url |  | Url Should work successfully | As Expected | Pass
Details |  | Link Details | 1. Click on Details 2. Click any container |  | Should show all details | As Expected | Pass
|  | Filter | Click day/week/month/year |  | Should show filtered data | As Expected | Pass
|  | Edit | 1. Click on container 2. Click edit button 3. Edit name and amount of incomplete payments |  | Should be edited | 1.Edit all status, but edit should be functionable only for incomplete payment stataus or amount should be blocked 2. when click edit and edit name ,mobile number is not prefilled | Fail
|  | Delete | 1. Click on container 2. Click edit button 3. Click Delete |  | Should be deleted successfully | As Expected | Pass

## Contacts
Product Name | Hishabee Business Manager App | Test Start Date |  | Test End Date |  | Developer Name |  | Device | Oneplus 8
Created By |  | Tawhiduzzaman Pavel | Reviewded By |  | Ratul Tazul | Version | 1.3.27 | OS | Android-11
Tester's Name |  | Tawhiduzzaman Pavel | Date Tested |  |  | Test Case(Pass/Fail/Warning) |  |  |  | TEST CASE SUMMARY
PASS
FAIL
Module | Test Case ID | Title | Steps/Action | Test Data | Expected Result | Actual Result | Status | Remarks |  | WARNING
TOTAL
Employee | TC-130 | Add Employee | 1. Click on Add New Employee 2. Fill employee informations 3. Upload Image 4. Click save button |  | Employee Name with mobile number and position should saved on Employee List | 1. In Details page salary not showing 2. No validation for same Employee ID | Fail
| TC-131 | Search Employee | 1. Type Employee name or number |  | Should get the filtered result | Need to mention search by number or name | Warning
|  | Edit Employee | 1. Click on Employee contact 2. Click on Edit 3. Edit Information 4. Click save |  | Should edited successfully | Salary not updated | Fail
|  | Delete Employee | 1. Click on Employee contact 2. Click on Edit 3. Edit on Delete button |  | Should be deleted successfully | As Expected | Pass
Customer | TC-132 | Add Customer | 1. Click on Add New Customer 2. Import Customer Contacts or fill customert informations 3. Click save button |  | Customer Name with mobile number should saved on Customer List | As Expected | Pass
| TC-133 | Search Customer | 1. Type customer name or number |  | Should get the filtered result | As Expected | Pass
|  | Edit Customer | 1. Click on customer contact 2. Click on Edit 3. Edit Information 4. Click save |  | Should edited successfully | Wnen edit Image or update image it gives error | Fail
|  | Delete Customer | 1. Click on customer contact 2. Click on Edit 3. Edit on Delete button |  | Should be deleted successfully | As Expected | Pass
Supplier | TC-134 | Add Supplier | 1. Click on Add New Supplier 2. Import Supplier Contacts or fill Supplier informations 3. Click save button |  | Supplier Name with mobile number should saved on Supplier List | As Expected | Pass
| TC-135 | Search Supplier | Type customer name or number |  | Should get the filtered result | As Expected | Pass
|  | Edit Suplier | 1. Click on supppplier contact 2. Click on Edit 3. Edit Information 4. Click save |  | Should edited successfully | Wnen edit Image or update image it gives error | Fail
|  | Delete Supplier | 1. Click on Supplier contact 2. Click on Edit 3. Edit on Delete button |  | Should be deleted successfully | As Expected | Pass

## SMS Marketing
Created By |  | Tawhiduzzaman Pavel | Reviewded By |  | Ratul Tazul | Version | 1.3.27 | OS | Android-11
Tester's Name |  | Tawhiduzzaman Pavel | Date Tested |  |  | Test Case(Pass/Fail/Warning) |  |  |  | TEST CASE SUMMARY
PASS
FAIL
Module | Test Case ID | Title | Steps/Action | Test Data | Expected Result | Actual Result | Status | Remarks |  | WARNING
TOTAL
SMS Marketing | TC-022 | Sent SMS | 1. Click on SMS Marketing 2. Input mobile number OR 3. Get the mobile number from customer/employee/supplier 4. Type message 5. Send the sms to the desired number | 1. Add Multiple Numbers from contact,manual entry,rployee.supplier 2. Total SMS 78 Sent SMS 6 | SMS should be sent successfully and sms left should be 72 | 1. Sms sent to same number,same sms multiple times if added multiple times from 2. Insufficecient sms balance text in bangla wrong spelling 3. Sms deducted 18 which is wrong | Fail
Add Customer | TC-023 | Add customer | 1. Click on Customer 2. Click Add Customer 3. Type Customer Name,Address, Mobile NO,Email or Import from contacts 4. Then Save the info |  | Should be added successfully | N/A
Add Employee | TC-024 | Add Employee | 1. Click on Employee 2. Click Add Employee 3. Type Employee Name,ID,Address, Mobile NO,Email,Monthly Salary 4. Then Save the info |  | Should be added successfully | N/A
Add Supplier | TC-025 | Add Supplier | 1. Click on Supplier 2. Click Add Supplier 3. Type Supplier Name,Address, Mobile NO,Email,Supplied Items 4. Then Save the info |  | Should be added successfully | N/A
Import From Contacts | TC-026 | Import Name and Mobile number from Mobile contact | 1. Click Customer/Employee/Supplier 2. Click Add Customer/Employee/Supplier 3. Click Import From Contact |  | Should be added successfully | N/A
Message History | TC-027 | Check Send SMS History | 1. Click SMS Marketing 2. Click top right Message History | Check with the send SMS | Should Show all sent sms with number and date | N/A
Buy SMS | TC-028 | Buy SMS | 1. Click Buy SMS 2. Choose Package 3. Pay with prefered way | SMS left 21 Buy SMS 100 | SMS should be added to total sms left(121) | Still in progress